## Resources
Resource_ID | Resource_Name | Role | Department | Weekly_Capacity_Hours
R001 | Resource_1 | Scrum Master | IT | 30
R002 | Resource_2 | Developer | Product | 30
R003 | Resource_3 | DevOps | Security | 35
R004 | Resource_4 | Project Coordinator | Engineering | 30
R005 | Resource_5 | Designer | IT | 40
R006 | Resource_6 | DevOps | PMO | 35
R007 | Resource_7 | DevOps | Creative | 40
R008 | Resource_8 | Scrum Master | Engineering | 35
R009 | Resource_9 | Designer | Creative | 40
R010 | Resource_10 | Project Coordinator | IT | 30
R011 | Resource_11 | Project Coordinator | Creative | 35
R012 | Resource_12 | Business Analyst | Creative | 40
R013 | Resource_13 | QA Analyst | Engineering | 30
R014 | Resource_14 | QA Analyst | PMO | 30
R015 | Resource_15 | QA Analyst | Product | 30
R016 | Resource_16 | QA Analyst | Engineering | 40
R017 | Resource_17 | Project Coordinator | Engineering | 40
R018 | Resource_18 | Designer | PMO | 35
R019 | Resource_19 | Scrum Master | Creative | 40
R020 | Resource_20 | Designer | Product | 40
R021 | Resource_21 | Project Coordinator | Product | 35
R022 | Resource_22 | QA Analyst | Creative | 40
R023 | Resource_23 | DevOps | Creative | 40
R024 | Resource_24 | Designer | PMO | 35
R025 | Resource_25 | Project Coordinator | Creative | 40

## Projects
Project_ID | Project_Name | Start_Date | End_Date | Priority
P001 | Mobile App Revamp | 2024-03-06 | 2024-08-19 | High
P002 | CRM Migration | 2024-03-25 | 2024-09-14 | Critical
P003 | Website Refresh | 2024-04-25 | 2024-10-17 | Critical
P004 | Security Audit Program | 2024-02-14 | 2024-06-25 | Critical
P005 | Cloud Optimization | 2024-03-03 | 2024-07-25 | Medium
P006 | Data Warehouse Build | 2024-04-30 | 2024-08-09 | Medium
P007 | AI Chatbot Deployment | 2024-04-22 | 2024-10-15 | High
P008 | New Feature Rollout | 2024-04-08 | 2024-10-01 | Critical
P009 | Network Upgrade | 2024-02-09 | 2024-05-17 | Critical
P010 | Customer Portal Redesign | 2024-02-09 | 2024-07-11 | Medium

## Tasks
Task_ID | Project_ID | Task_Name | Assigned_To | Start_Date | End_Date | Planned_Hours | Hours_Logged | Status
T001 | P008 | Task_1 | R017 | 2024-05-01 | 2024-06-23 | 99 | 0 | In Progress
T002 | P001 | Task_2 | R007 | 2024-03-12 | 2024-03-25 | 93 | 59 | Completed
T003 | P004 | Task_3 | R022 | 2024-02-20 | 2024-04-18 | 86 | 52 | Not Started
T004 | P004 | Task_4 | R002 | 2024-03-12 | 2024-05-06 | 117 | 71 | In Progress
T005 | P003 | Task_5 | R008 | 2024-04-26 | 2024-05-11 | 34 | 0 | Not Started
T006 | P001 | Task_6 | R024 | 2024-03-07 | 2024-04-09 | 52 | 42 | Completed
T007 | P003 | Task_7 | R017 | 2024-04-25 | 2024-05-29 | 95 | 64 | Not Started
T008 | P001 | Task_8 | R001 | 2024-03-28 | 2024-05-16 | 100 | 86 | In Progress
T009 | P006 | Task_9 | R016 | 2024-05-01 | 2024-05-30 | 77 | 0 | Completed
T010 | P001 | Task_10 | R009 | 2024-03-31 | 2024-05-19 | 110 | 82 | Not Started
T011 | P006 | Task_11 | R004 | 2024-05-01 | 2024-06-08 | 120 | 0 | Not Started
T012 | P009 | Task_12 | R019 | 2024-03-05 | 2024-04-15 | 85 | 42 | In Progress
T013 | P005 | Task_13 | R020 | 2024-03-29 | 2024-05-19 | 22 | 18 | Completed
T014 | P001 | Task_14 | R009 | 2024-03-08 | 2024-03-26 | 40 | 11 | Completed
T015 | P004 | Task_15 | R017 | 2024-02-16 | 2024-03-12 | 49 | 45 | In Progress
T016 | P002 | Task_16 | R019 | 2024-04-08 | 2024-05-27 | 99 | 67 | Completed
T017 | P007 | Task_17 | R009 | 2024-05-25 | 2024-07-22 | 20 | 8 | In Progress
T018 | P003 | Task_18 | R004 | 2024-05-27 | 2024-07-22 | 31 | 25 | Not Started
T019 | P003 | Task_19 | R025 | 2024-05-09 | 2024-05-25 | 47 | 5 | In Progress
T020 | P008 | Task_20 | R010 | 2024-05-12 | 2024-07-02 | 68 | 42 | Completed
T021 | P007 | Task_21 | R014 | 2024-05-24 | 2024-06-04 | 94 | 41 | Completed
T022 | P010 | Task_22 | R006 | 2024-02-15 | 2024-04-07 | 81 | 15 | Not Started
T023 | P010 | Task_23 | R012 | 2024-02-27 | 2024-04-21 | 67 | 15 | Not Started
T024 | P002 | Task_24 | R010 | 2024-04-06 | 2024-06-04 | 106 | 0 | In Progress
T025 | P001 | Task_25 | R014 | 2024-04-15 | 2024-05-26 | 79 | 4 | Completed
T026 | P002 | Task_26 | R001 | 2024-04-12 | 2024-04-23 | 67 | 58 | Not Started
T027 | P008 | Task_27 | R007 | 2024-04-15 | 2024-05-31 | 67 | 8 | Not Started
T028 | P006 | Task_28 | R013 | 2024-05-07 | 2024-06-02 | 35 | 14 | Completed
T029 | P007 | Task_29 | R007 | 2024-04-28 | 2024-05-09 | 99 | 0 | Not Started
T030 | P008 | Task_30 | R010 | 2024-04-30 | 2024-06-08 | 38 | 21 | In Progress
T031 | P009 | Task_31 | R016 | 2024-03-06 | 2024-04-16 | 107 | 78 | Not Started
T032 | P008 | Task_32 | R020 | 2024-04-24 | 2024-06-08 | 74 | 64 | Completed
T033 | P010 | Task_33 | R004 | 2024-02-13 | 2024-03-16 | 42 | 0 | Not Started
T034 | P007 | Task_34 | R003 | 2024-04-27 | 2024-06-19 | 102 | 65 | In Progress
T035 | P004 | Task_35 | R023 | 2024-03-06 | 2024-04-13 | 42 | 35 | Not Started
T036 | P009 | Task_36 | R025 | 2024-03-07 | 2024-03-23 | 62 | 17 | Completed
T037 | P005 | Task_37 | R006 | 2024-03-13 | 2024-04-21 | 110 | 65 | Completed
T038 | P003 | Task_38 | R015 | 2024-05-23 | 2024-07-18 | 23 | 0 | In Progress
T039 | P003 | Task_39 | R013 | 2024-05-27 | 2024-06-09 | 81 | 49 | Completed
T040 | P007 | Task_40 | R023 | 2024-05-22 | 2024-06-24 | 90 | 6 | Not Started
T041 | P004 | Task_41 | R018 | 2024-03-24 | 2024-04-15 | 71 | 0 | In Progress
T042 | P001 | Task_42 | R011 | 2024-04-04 | 2024-05-17 | 111 | 0 | In Progress
T043 | P003 | Task_43 | R004 | 2024-04-26 | 2024-05-31 | 47 | 9 | In Progress
T044 | P004 | Task_44 | R004 | 2024-03-09 | 2024-04-23 | 118 | 0 | In Progress
T045 | P010 | Task_45 | R019 | 2024-02-21 | 2024-04-02 | 98 | 20 | Completed
T046 | P007 | Task_46 | R016 | 2024-05-08 | 2024-06-19 | 92 | 1 | Not Started
T047 | P002 | Task_47 | R012 | 2024-03-25 | 2024-05-05 | 88 | 0 | Completed
T048 | P002 | Task_48 | R025 | 2024-05-01 | 2024-06-11 | 106 | 0 | In Progress
T049 | P005 | Task_49 | R017 | 2024-04-01 | 2024-04-12 | 30 | 19 | Not Started
T050 | P007 | Task_50 | R009 | 2024-06-01 | 2024-07-31 | 112 | 92 | In Progress
T051 | P007 | Task_51 | R015 | 2024-05-10 | 2024-05-29 | 21 | 7 | Not Started
T052 | P006 | Task_52 | R002 | 2024-06-03 | 2024-07-07 | 92 | 6 | In Progress
T053 | P008 | Task_53 | R021 | 2024-04-16 | 2024-05-26 | 108 | 70 | Not Started
T054 | P005 | Task_54 | R011 | 2024-03-22 | 2024-04-22 | 102 | 0 | In Progress
T055 | P007 | Task_55 | R017 | 2024-04-27 | 2024-06-08 | 101 | 25 | Completed
T056 | P003 | Task_56 | R017 | 2024-06-04 | 2024-06-19 | 59 | 30 | Completed
T057 | P004 | Task_57 | R017 | 2024-03-02 | 2024-03-15 | 34 | 10 | In Progress
T058 | P004 | Task_58 | R011 | 2024-03-07 | 2024-03-21 | 62 | 52 | In Progress
T059 | P008 | Task_59 | R010 | 2024-05-07 | 2024-05-25 | 111 | 30 | Not Started
T060 | P005 | Task_60 | R011 | 2024-03-13 | 2024-03-29 | 50 | 2 | Completed
T061 | P006 | Task_61 | R006 | 2024-05-22 | 2024-06-09 | 37 | 2 | Completed
T062 | P007 | Task_62 | R013 | 2024-05-13 | 2024-06-09 | 112 | 0 | Completed
T063 | P010 | Task_63 | R023 | 2024-02-29 | 2024-04-26 | 71 | 34 | Completed
T064 | P010 | Task_64 | R021 | 2024-02-13 | 2024-03-17 | 59 | 48 | In Progress
T065 | P006 | Task_65 | R015 | 2024-05-30 | 2024-06-14 | 43 | 19 | Not Started
T066 | P001 | Task_66 | R004 | 2024-03-28 | 2024-04-17 | 65 | 10 | Not Started
T067 | P009 | Task_67 | R011 | 2024-02-24 | 2024-04-12 | 69 | 9 | Completed
T068 | P003 | Task_68 | R012 | 2024-05-15 | 2024-06-06 | 83 | 65 | Not Started
T069 | P006 | Task_69 | R009 | 2024-05-09 | 2024-06-14 | 66 | 23 | Not Started
T070 | P004 | Task_70 | R023 | 2024-02-29 | 2024-04-25 | 98 | 51 | Completed
T071 | P010 | Task_71 | R002 | 2024-02-18 | 2024-03-10 | 28 | 4 | In Progress
T072 | P003 | Task_72 | R011 | 2024-05-28 | 2024-07-13 | 34 | 9 | Not Started
T073 | P001 | Task_73 | R013 | 2024-04-05 | 2024-05-16 | 99 | 0 | Completed
T074 | P010 | Task_74 | R020 | 2024-02-14 | 2024-04-01 | 85 | 22 | In Progress
T075 | P008 | Task_75 | R006 | 2024-05-04 | 2024-06-07 | 87 | 74 | In Progress
T076 | P010 | Task_76 | R005 | 2024-02-16 | 2024-04-09 | 84 | 0 | Not Started
T077 | P007 | Task_77 | R010 | 2024-05-21 | 2024-07-15 | 21 | 0 | In Progress
T078 | P004 | Task_78 | R006 | 2024-02-15 | 2024-03-05 | 74 | 63 | In Progress
T079 | P008 | Task_79 | R002 | 2024-05-08 | 2024-06-02 | 28 | 11 | Not Started
T080 | P003 | Task_80 | R023 | 2024-05-27 | 2024-07-10 | 27 | 10 | Not Started
T081 | P009 | Task_81 | R011 | 2024-03-13 | 2024-04-07 | 37 | 37 | Not Started
T082 | P009 | Task_82 | R004 | 2024-02-24 | 2024-03-11 | 79 | 73 | Completed
T083 | P004 | Task_83 | R021 | 2024-03-09 | 2024-04-09 | 99 | 49 | Completed
T084 | P009 | Task_84 | R017 | 2024-02-19 | 2024-04-01 | 33 | 0 | Not Started
T085 | P004 | Task_85 | R006 | 2024-03-09 | 2024-03-31 | 58 | 49 | In Progress
T086 | P003 | Task_86 | R013 | 2024-05-15 | 2024-06-13 | 32 | 2 | In Progress
T087 | P005 | Task_87 | R017 | 2024-04-03 | 2024-04-30 | 49 | 41 | Completed
T088 | P009 | Task_88 | R022 | 2024-02-15 | 2024-02-26 | 97 | 72 | Not Started
T089 | P004 | Task_89 | R013 | 2024-03-22 | 2024-04-03 | 102 | 99 | Completed
T090 | P005 | Task_90 | R023 | 2024-04-02 | 2024-05-16 | 26 | 0 | Not Started
T091 | P003 | Task_91 | R020 | 2024-05-15 | 2024-05-27 | 108 | 95 | Not Started
T092 | P009 | Task_92 | R006 | 2024-02-14 | 2024-04-07 | 79 | 53 | Not Started
T093 | P006 | Task_93 | R023 | 2024-05-17 | 2024-06-29 | 92 | 39 | Completed
T094 | P001 | Task_94 | R015 | 2024-03-25 | 2024-05-16 | 35 | 18 | Not Started
T095 | P004 | Task_95 | R014 | 2024-03-06 | 2024-04-01 | 88 | 13 | Completed
T096 | P004 | Task_96 | R014 | 2024-02-22 | 2024-04-16 | 41 | 13 | In Progress
T097 | P006 | Task_97 | R013 | 2024-05-30 | 2024-07-18 | 52 | 15 | In Progress
T098 | P008 | Task_98 | R007 | 2024-05-08 | 2024-06-23 | 63 | 42 | In Progress
T099 | P010 | Task_99 | R021 | 2024-03-10 | 2024-04-03 | 118 | 34 | Completed
T100 | P003 | Task_100 | R022 | 2024-05-14 | 2024-06-06 | 88 | 0 | In Progress
T101 | P002 | Task_101 | R001 | 2024-03-26 | 2024-04-17 | 60 | 26 | In Progress
T102 | P006 | Task_102 | R015 | 2024-05-04 | 2024-06-09 | 80 | 0 | Not Started
T103 | P005 | Task_103 | R019 | 2024-04-08 | 2024-04-26 | 47 | 9 | In Progress
T104 | P002 | Task_104 | R021 | 2024-05-01 | 2024-06-08 | 55 | 24 | In Progress
T105 | P004 | Task_105 | R005 | 2024-03-21 | 2024-04-19 | 49 | 4 | In Progress
T106 | P010 | Task_106 | R020 | 2024-03-05 | 2024-04-17 | 72 | 45 | Completed
T107 | P001 | Task_107 | R009 | 2024-03-21 | 2024-04-08 | 99 | 44 | Not Started
T108 | P008 | Task_108 | R013 | 2024-05-03 | 2024-06-12 | 68 | 38 | Not Started
T109 | P001 | Task_109 | R018 | 2024-04-08 | 2024-04-23 | 97 | 0 | Completed
T110 | P001 | Task_110 | R002 | 2024-03-30 | 2024-05-24 | 75 | 10 | In Progress
T111 | P002 | Task_111 | R012 | 2024-04-26 | 2024-05-29 | 86 | 0 | In Progress
T112 | P010 | Task_112 | R003 | 2024-03-09 | 2024-05-05 | 109 | 106 | Not Started
T113 | P008 | Task_113 | R002 | 2024-04-16 | 2024-06-06 | 38 | 23 | Completed
T114 | P001 | Task_114 | R020 | 2024-03-15 | 2024-05-05 | 57 | 0 | Not Started
T115 | P009 | Task_115 | R018 | 2024-02-14 | 2024-04-07 | 105 | 15 | Not Started
T116 | P001 | Task_116 | R010 | 2024-04-07 | 2024-05-29 | 54 | 19 | In Progress
T117 | P006 | Task_117 | R022 | 2024-05-06 | 2024-06-23 | 66 | 22 | In Progress
T118 | P005 | Task_118 | R016 | 2024-03-21 | 2024-05-02 | 96 | 0 | Not Started
T119 | P001 | Task_119 | R011 | 2024-04-02 | 2024-05-22 | 21 | 4 | Completed
T120 | P001 | Task_120 | R022 | 2024-03-10 | 2024-05-03 | 89 | 34 | In Progress
T121 | P007 | Task_121 | R008 | 2024-05-03 | 2024-05-23 | 98 | 23 | Completed
T122 | P006 | Task_122 | R022 | 2024-05-11 | 2024-06-08 | 22 | 0 | Not Started
T123 | P004 | Task_123 | R019 | 2024-02-28 | 2024-04-03 | 28 | 0 | Not Started
T124 | P010 | Task_124 | R003 | 2024-02-24 | 2024-03-19 | 90 | 90 | Completed
T125 | P007 | Task_125 | R003 | 2024-05-24 | 2024-06-20 | 94 | 88 | Completed
T126 | P009 | Task_126 | R017 | 2024-03-05 | 2024-04-11 | 120 | 66 | Not Started
T127 | P008 | Task_127 | R024 | 2024-05-01 | 2024-05-14 | 93 | 37 | In Progress
T128 | P010 | Task_128 | R021 | 2024-03-08 | 2024-03-28 | 83 | 67 | In Progress
T129 | P003 | Task_129 | R001 | 2024-05-11 | 2024-07-05 | 43 | 0 | Completed
T130 | P007 | Task_130 | R019 | 2024-06-01 | 2024-06-27 | 76 | 52 | In Progress
T131 | P007 | Task_131 | R009 | 2024-05-06 | 2024-06-07 | 116 | 112 | In Progress
T132 | P010 | Task_132 | R001 | 2024-03-07 | 2024-04-05 | 23 | 0 | Completed
T133 | P008 | Task_133 | R019 | 2024-04-24 | 2024-06-16 | 54 | 9 | In Progress
T134 | P006 | Task_134 | R017 | 2024-06-08 | 2024-07-17 | 104 | 36 | Not Started
T135 | P008 | Task_135 | R010 | 2024-05-01 | 2024-06-06 | 34 | 19 | Completed
T136 | P007 | Task_136 | R004 | 2024-05-19 | 2024-07-06 | 79 | 21 | Not Started
T137 | P007 | Task_137 | R015 | 2024-05-31 | 2024-07-29 | 111 | 65 | Completed
T138 | P006 | Task_138 | R006 | 2024-05-09 | 2024-06-02 | 105 | 0 | Not Started
T139 | P007 | Task_139 | R015 | 2024-05-23 | 2024-07-17 | 112 | 0 | In Progress
T140 | P005 | Task_140 | R011 | 2024-04-08 | 2024-05-13 | 58 | 8 | In Progress
T141 | P006 | Task_141 | R022 | 2024-04-30 | 2024-06-04 | 95 | 37 | Not Started
T142 | P002 | Task_142 | R001 | 2024-04-17 | 2024-05-17 | 97 | 46 | Not Started
T143 | P006 | Task_143 | R003 | 2024-06-02 | 2024-07-20 | 81 | 51 | In Progress
T144 | P002 | Task_144 | R020 | 2024-03-26 | 2024-04-27 | 23 | 19 | Completed
T145 | P001 | Task_145 | R001 | 2024-03-27 | 2024-05-01 | 81 | 3 | Not Started
T146 | P008 | Task_146 | R021 | 2024-05-14 | 2024-06-06 | 48 | 28 | Not Started
T147 | P006 | Task_147 | R010 | 2024-05-25 | 2024-07-10 | 96 | 37 | In Progress
T148 | P002 | Task_148 | R017 | 2024-04-07 | 2024-05-23 | 66 | 19 | Not Started
T149 | P004 | Task_149 | R018 | 2024-03-24 | 2024-04-17 | 46 | 31 | In Progress
T150 | P005 | Task_150 | R019 | 2024-03-16 | 2024-04-27 | 40 | 10 | Completed
T151 | P006 | Task_151 | R021 | 2024-05-11 | 2024-07-03 | 45 | 7 | Not Started
T152 | P008 | Task_152 | R020 | 2024-04-08 | 2024-06-07 | 113 | 87 | Completed
T153 | P004 | Task_153 | R001 | 2024-03-24 | 2024-04-08 | 78 | 53 | Completed
T154 | P003 | Task_154 | R009 | 2024-05-20 | 2024-07-08 | 22 | 19 | In Progress
T155 | P001 | Task_155 | R019 | 2024-03-29 | 2024-05-08 | 68 | 9 | Not Started
T156 | P003 | Task_156 | R025 | 2024-05-24 | 2024-07-14 | 28 | 1 | In Progress
T157 | P009 | Task_157 | R003 | 2024-03-13 | 2024-05-07 | 57 | 56 | Completed
T158 | P009 | Task_158 | R007 | 2024-02-13 | 2024-03-20 | 36 | 17 | In Progress
T159 | P004 | Task_159 | R002 | 2024-03-06 | 2024-04-14 | 120 | 91 | Completed
T160 | P006 | Task_160 | R021 | 2024-05-19 | 2024-07-12 | 102 | 78 | Not Started
T161 | P004 | Task_161 | R001 | 2024-03-05 | 2024-03-22 | 54 | 5 | Not Started
T162 | P009 | Task_162 | R023 | 2024-03-19 | 2024-04-06 | 64 | 10 | Completed
T163 | P004 | Task_163 | R010 | 2024-03-20 | 2024-05-17 | 22 | 12 | Completed
T164 | P003 | Task_164 | R024 | 2024-04-29 | 2024-06-12 | 116 | 22 | In Progress
T165 | P007 | Task_165 | R022 | 2024-05-14 | 2024-06-23 | 104 | 96 | Completed
T166 | P003 | Task_166 | R024 | 2024-05-02 | 2024-05-12 | 31 | 0 | In Progress
T167 | P003 | Task_167 | R010 | 2024-05-31 | 2024-07-23 | 88 | 59 | Completed
T168 | P004 | Task_168 | R011 | 2024-02-19 | 2024-03-11 | 105 | 53 | Completed
T169 | P001 | Task_169 | R011 | 2024-04-02 | 2024-05-13 | 103 | 80 | Completed
T170 | P002 | Task_170 | R022 | 2024-03-27 | 2024-04-14 | 107 | 0 | Not Started
T171 | P007 | Task_171 | R025 | 2024-05-06 | 2024-06-25 | 54 | 10 | Not Started
T172 | P002 | Task_172 | R017 | 2024-04-30 | 2024-06-25 | 99 | 15 | Completed
T173 | P002 | Task_173 | R018 | 2024-04-14 | 2024-05-02 | 84 | 26 | Completed
T174 | P007 | Task_174 | R015 | 2024-04-28 | 2024-05-28 | 49 | 43 | In Progress
T175 | P001 | Task_175 | R019 | 2024-03-13 | 2024-05-09 | 53 | 38 | In Progress
T176 | P007 | Task_176 | R008 | 2024-04-24 | 2024-05-12 | 41 | 0 | Completed
T177 | P003 | Task_177 | R013 | 2024-05-04 | 2024-05-20 | 102 | 48 | In Progress
T178 | P001 | Task_178 | R004 | 2024-04-02 | 2024-04-12 | 108 | 104 | Not Started
T179 | P007 | Task_179 | R001 | 2024-05-04 | 2024-07-03 | 68 | 0 | Not Started
T180 | P003 | Task_180 | R009 | 2024-05-12 | 2024-06-07 | 92 | 26 | In Progress
T181 | P005 | Task_181 | R019 | 2024-03-29 | 2024-05-09 | 81 | 0 | In Progress
T182 | P005 | Task_182 | R013 | 2024-03-14 | 2024-05-04 | 73 | 0 | In Progress
T183 | P009 | Task_183 | R014 | 2024-03-16 | 2024-05-09 | 61 | 25 | Not Started
T184 | P005 | Task_184 | R014 | 2024-04-09 | 2024-05-18 | 112 | 5 | Completed
T185 | P009 | Task_185 | R016 | 2024-03-13 | 2024-05-02 | 55 | 42 | In Progress
T186 | P002 | Task_186 | R024 | 2024-04-08 | 2024-05-01 | 75 | 10 | Not Started
T187 | P009 | Task_187 | R013 | 2024-02-19 | 2024-03-04 | 59 | 0 | Not Started
T188 | P009 | Task_188 | R003 | 2024-03-03 | 2024-04-25 | 43 | 8 | Not Started
T189 | P007 | Task_189 | R018 | 2024-04-24 | 2024-05-29 | 89 | 60 | Not Started
T190 | P007 | Task_190 | R008 | 2024-05-04 | 2024-06-19 | 49 | 33 | Completed
T191 | P005 | Task_191 | R020 | 2024-03-19 | 2024-04-08 | 23 | 11 | Completed
T192 | P001 | Task_192 | R002 | 2024-04-06 | 2024-04-28 | 90 | 53 | Completed
T193 | P001 | Task_193 | R015 | 2024-03-27 | 2024-04-17 | 77 | 30 | In Progress
T194 | P008 | Task_194 | R009 | 2024-05-10 | 2024-06-05 | 26 | 26 | In Progress
T195 | P004 | Task_195 | R006 | 2024-03-09 | 2024-05-02 | 107 | 53 | Completed
T196 | P005 | Task_196 | R003 | 2024-03-14 | 2024-05-11 | 26 | 0 | Not Started
T197 | P009 | Task_197 | R019 | 2024-02-18 | 2024-02-29 | 23 | 2 | Completed
T198 | P010 | Task_198 | R025 | 2024-03-14 | 2024-04-23 | 75 | 0 | Completed
T199 | P010 | Task_199 | R011 | 2024-02-15 | 2024-02-25 | 29 | 6 | Completed
T200 | P009 | Task_200 | R001 | 2024-02-18 | 2024-02-29 | 57 | 56 | Completed